## Start
Page:
1
Version:
1
Class:
I
Name of document: |  |  | Type: | Reg.no:
SWU Planning and Status |  |  | Template | TQ-15-0038
Issued by: |  |  | Sign: | Date:
Anna Mörkerdal |  |  | AMl | 2015-10-06
Approved by: |  |  | Sign: | Date:
Dennis Kristensson |  |  | DKn | 2015-10-06
Project Information
Project No.: |  | Document No.:
Customer: |  | Document Creation date:
Project Manager T-Engineering:
Document Update Logg
Date: | Document updated by:
Revision History
Change |  | Issuer |  | Date

## A15 SWU Status (hidden)
Date: |  |  |  | SWU Modell = 30% MIL Test = 50% HIL Test = 70 % Calibration = 90 % SWU Released = 100 %
Ver:
SWU | version | Domain | Owner | Status in % | Inital SW | 50% cal | 65% cal | 80% cal | 99% cal | 100%cal
[5 empty] | 2014-05-10 | 2014-08-22 | 2015-01-09 | 2015-05-01 | 2015-09-04 | 2015-09-30
BSWE_BasicSoftwareErrorhandling | CW523.1(3) | BSW | Fredrik Svan | 50 | X
CANE_AD_CANError | CW527.1(5) | Diagnostics | Robert Andersson
ComM_CommunicationsManager | CW512(2) | BSW | Robert Andersson
Dcm_EMS_EMS | CW526(6) | BSW | Robert Andersson
Dem_EMS_EMS | CW526(18) | BSW | Robert Andersson
DEME_DemExtension | CW527(12) | BSW | Robert Andersson
EcuM_EMS_EMS | CW512(3) | BSW | Jan Björn
EPOS_EnginePositioning | CW527(30) | BSW | Fredrik Svan
FACT_SwVersionInformation | CW527.1(12) | BSW | Mathias Stålek
FINC_FuelINjectorControl | CW526(10) | BSW | Fredrik Svan
HWDI_HardWareDiagnosticInfo | CW527(6) | BSW | Sebastian Wallman
ICCO_IgnitionCoilCOntrol | CW527(11) | BSW | Fredrik Svan
IMMO_AD_Immobilizer | CW527(11) | Torque | Fredrik Assarsson
KSDC_KnockSensorDeCoding | CW526(12) | BSW | Fredrik Svan
MEMO_MEMOry | CW527(6) | BSW | Fredrik Svan
MUTR_MonitoringUnitconTRoller | CW528(11) | BSW | Fredrik Svan
PWRM_AE_PowerMode | CW520(8) | Torque | Fredrik Behrendtz
BASS_BrakeSensorSystem | CSW20(20) | Torque | Emil Hilding
VSPE_VehicleSpeedEstimation | CW511(44) | Torque | Fredrik Assarsson
VODO_VehicleOdometer | CW525(7) | Torque | Fredrik Assarsson
VLOT_VehicleLOngitudinalTorque | CW520(18) | Torque | Fredrik Assarsson
AILM_AIrLiMits | CW449(9) | Combustion | Joel Lejonklou
ARES_AiREStimation | CW525(53) | Combustion | Per Andersson
CATC_CatalystControl | CW514(12) | Combustion | Fredrik Andersson
DYNO_DYNO | CW508(18) | Combustion | Andreas Gunnarsson
EARS_EngineArbitratedRotationalSpeed | CW503(10) | Combustion | Andreas Gunnarsson
ECOM_EngineControlManager | CW506.1(5) | Combustion | Andreas Gunnarsson
ECPC_ExhaustCamPostionControl | CW524(7) | Combustion | Per Darnfors
EITC_EngineIndicatedTorqueCalculation | CW521(35) | Combustion | Per Andersson
EOLT_EngineOiLTemperature | CW508(15) | Combustion | Per Darnfors
ETME_ExhaustTemperatureMeasurementAndEstimation | CW520(9) | Combustion | Joel Lejonklou
EXPE_ExhaustPressureEstimator | CSW21.2(3) | Thermal | Chunjiao Zhang
FINT_FuelINjectorTiming | CW520.1(30) | Diagnostics | Chunjiao Zhang
FPCR_FuelPumpControl | CW521.1(15) | Combustion | Tianfang Zhao
FUEL_Fuel | CW526(60) | Combustion | Claes Östberg
IASH_IntakeAirSystemHarmonization | CW519(17) | Combustion | Xue Lei
ICPC_IntakeCamPositionControl | CW524(26) | Combustion | Per Darnfors
ITCC_EMS_EMS_ICETorqueCapabilityAtCrankShaft | CW503.1(15) | Combustion | Joel Lejonklou
KOCO_KnOckCOntrol | CW525p1(18) | Combustion | Andreas Gunnarsson
OCTA_OctaneAdaption | CW525(9) | Combustion | Andreas Gunnarsson
OXYS_OxygenSensor | CW520(30) | Diagnostics | Liuchun Yang
PUCO_PUrgeCOntrol | CW526.1(34) | Combustion | Claes Östberg
SPRK_SPaRK | CW525(30) | Combustion | Andreas Gunnarsson
TPSC_ThrottlePositionSensingAndControl | CW519p1(28) | Combustion | Per Darnfors
VAVM_VAriableValveMaster | CW509(11) | Combustion | Per Darnfors
VLIM_VariableLengthIntakeManifold | CW518.2(8) | Combustion | Joel Lejonklou
ACBD_AC_ButtonDiagnosis | CW516(2) | Diagnostics | Stefan Bergström
ACOD_AC_ClutchControlDiagnosis | CW450(17) | Diagnostics | Mikael Andersson
ACPD_ACPressureDiagnosis | CW450(10) | Diagnostics | Feng Xu
ACRD_AirConditionRequestDiagnosis | CW513(12) | Diagnostics | Feng Xu
ACTD_AirCondTemperatureDiagnosis | CW450.2(20) | Diagnostics | Feng Xu
APSS_AcceleratorPedalSensorSystem | CW520.1(22) | Torque | Emil Hilding
BPPD_BrakePedalPositionDiagnosis | CW518(24) | Diagnostics | Stefan Bergström
BVAD_BrakeVAcuumSensorDiagnostic | CW516(17) | Diagnostics | Stefan Bergström
CACD_CAmControlDiagnosis | CW505(16) | Diagnostics | Stefan Bergström
CAMD_CamPositionDiagnosis | CW526.2(14) | Diagnostics | Stefan Bergström
CASD_CAm_exhaustSensorDiagnosis | CW526.1(3) | Diagnostics | Stefan Bergström
CATD_CatalyticEfficiencyDiagnosis | CW526(9) | Diagnostics | Ronnie Magnusson
CCSD_CruiseControlSystemDiagnosis | CW506(12) | Diagnostics | Feng Xu
CECD_CamExhaustControlDiagnosis | CW526.1(8) | Diagnostics | Stefan Bergström
CFMN_ControlFlowMonitoring | CW527(21) | Diagnostics | Fredrik Andersson
COLD_CoreOutofLimDiagnosis | CW525(27) | Diagnostics | Mikael Andersson
CPPD_ClutchPedalPositionDiagnosis | CW524(28) | Diagnostics | Mikael Andersson
CRAD_CrankAngleDiagnosis | CW509(15) | Diagnostics | Stefan Bergström
CSIN_CrashSignalINterpretation | CW519(13) | Torque | Ronnie Magnusson
CWTD_CoolantWaterTemperature_sensorDiagnosis | CW515(23) | Diagnostics | Mikael Andersson
ESDD_EngineSpeedDisplayDiagnosis | CW450(13) | Diagnostics | Feng Xu
ESID_AD_ExtendedServicesID | CW526.4(27) | Diagnostics | Mikael Andersson
ETHD_ElectricTHermostatDiagnosis | CW525(5) | Diagnostics | Stefan Bergström
EVPD_EvaporativePurgeValveDiagnosis | CW450.3(20) | Diagnostics | Long Qin
FAND_FanOutputDiagnosis | CW511(13) | Diagnostics | Cristian Salazar
FDMA_FunctionalDegradationMAnager | CW524.1(20) | Diagnostics | Christian Fransson
FPCD_FuelPumpControlDiagnosis | CW450.1(21) | Diagnostics | Cristian Salazar
FUID_FuelInjectorDiagnosis | CW450(12) | Diagnostics | Cristian Salazar
FUSD_FuelSystemDiagnosis | CW526(4) | Diagnostics | Cristian Salazar
HAMF_AD_HArdwareMonitoringFunction | CW522.3(5a1) | Diagnostics | Mikael Andersson
HOOD_HOOd switch Diagnos | CW516(13) | Diagnostics | Mikael Andersson
IGCD_IgnitionCoilDiagnosis | CW505.1(14) | Diagnostics | Long Qin
KNOD_KnockSensorDiagnosis | CW504(15) | Diagnostics | Stefan Bergström
LINE_EMS_EMS | CW525(4) | Diagnostics | Ronnie Magnusson
LSID_EMS_EMS | CW526.3(25) | Diagnostics | Mikael Andersson
MAPD_ManifoldAbsolutePressureDiagnosis | CW535.1(25) | Diagnostics | Feng Xu
MATD_MAnifoldTemperatureDiagnosis | CW508(33) | Diagnostics | Long Qin
MILD_MalfunctionIndicatorLampDiagnosis | CW516(11) | Diagnostics | Stefan Bergström
MSFD_MisfireDiagnosis | CW525(7) | Diagnostics | Fredrik Andersson
NGSD_NeutralGearSensorDiagnosis | CW521(4) | Diagnostics | Stefan Bergström
OSDD_OxygenSensorDeteriorationDiagnosis | CW525(17) | Diagnostics | Cristian Salazar
OSHD_OxygenSensorHeaterDiagnosis | CW525(15) | Diagnostics | Cristian Salazar
PRCD_PowerRelayControlDiagnosis | CW525.1(2) | Diagnostics | Feng Xu
SRCD_StarterRelayCircuitDiagnosis | CW526(21) | Diagnostics | Cristian Salazar
SSSD_StartStopSensorDiagnosis | CW522.1(7) | Diagnostics | Mikael Andersson
SYVD_SystemVoltageDiagnosis | CW513(20) | Diagnostics | Cristian Salazar
TPSD_ThrottlePositionDiagnosis | CW526(19) | Diagnostics | Stefan Bergström
V5RD_Regulated5VoltDiagnosis | CW450(19) | Diagnostics | Cristian Salazar
VILD_VariableIntakeLengthDiagnosis | CW507.1(4) | Diagnostics | Stefan Bergström
ACCP_AcceleratorPedalmap | CW504(27) | Torque | Emil Hilding
ACRC_AirConditionRelayControl | CW525(14) | Torque | Kai Wang
AJTC_AntiJerkTorqueControl | CW521(6) | Torque | Magnus Källvik
ATLC_AutomaticTransmissionLoadCalculation | CW519(2) | Torque | Fredrik Behrendtz
CACE_ControllerAfterrunAndCanEnable | CW514(36a7) | Torque | Fredrik Behrendtz
CIDI_CruiseIndicatorDIsplay | CW450.1(5) | Torque | Long Qin
CRSC_CruiseControl | CW523(34) | Torque | Tianfang Zhao
DCWT_DirectionControlWheelTorque | CW506(21) | Torque | Fredrik Behrendtz
DIPR_DIfferentialPRotection | CW518(8) | Torque | Olof Martander
DOSR_DetermineOptimalSystemRequest | CW510_NH(34a4) | Torque | Magnus Källvik
DPSC_DeterminePropulsionSystemCapability | CW520.1(37) | Torque | Emil Hilding
DTOS_DriveabilityTorqueShaping | CW525(27) | Torque | Magnus Källvik
ESDI_EngineSpeedDIsplay | CW519(4) | Torque | Feng Xu
FCDI_FuelConsumptionDIsplay | CW509.3(8) | Torque | Feng Xu
GEVC_GEneratorVoltageControl | CW514.1(18) | Torque | Kai Wang
HETE_HybridElectricTorqueExecutor | CW448(49) | Torque | Johan Larsson
LVEM_LowVoltageEnergyManagement | CW515(37) | Torque | Olof Martander
MAVS_MaximumVehicleSpeed | CW515.1(32) | Torque | Olof Martander
PDLS_BothPedalShaping | CW450(20) | Torque | Emil Hilding
POLC_P1LoadCalculation | CW514(18) | Torque | Fredrik Behrendtz
PORS_P1RotationalSpeed | CSW25.5(19) | Torque | Fredrik Behrendtz
SILT_AD_SoftwareInterfaceLevelTwo | CW523(6) | Diagnostics | Christian Fransson
SPAR_EMS_EMS | CW521(10) | Torque | Fredrik Behrendtz
SSDI_StartStopDisplayInformation | CW520.2(7) | Torque | Emil Hilding
SSDL_StartStopDeterminationLogic | CW520(55) | Torque | Johan Larsson
SSSC_StartStopSequenceControl | CW524(42) | Torque | Johan Larsson
SSSM_StartStopStateMachine | CW503(36) | Torque | Johan Larsson
SSTD_StartStopTypeDetermination | CW522(19) | Torque | Johan Larsson
STCW_SystemTorqueCapabilities | CW519(39) | Torque | Magnus Källvik
SWIN_EMS_EMS | CW528(61) | Torque | Fredrik Behrendtz
TIRC_WheelToTransmissionInputandResponseControl | CW514(28) | Torque | Magnus Källvik
TISC_TransmissionInputSpeedControl | CW521.1(59) | Torque | Johan Larsson
TQMS_TorqueMonitoring | CW526.2(47) | Diagnostics | Christian Fransson
VTAR_VehicleTorqueArbitration | CW509(26) | Torque | Fredrik Behrendtz
WTDA_WheelTorqueDistribution | CSW20(9) | Torque | Magnus Källvik
GERC_GearEstimationAndRatioCalulation | CW511(29) | Torque | Per Darnfors
TCAP_TransmissionCapabilities | CW520(26) | Torque | Christian Fransson
TTSS_TransmissionTorqueandSpeedSupport | CW520(32a4) | Torque | Per Darnfors
CTDI_CoolantTempDIsplay | CW519(9) | Torque | Long Qin
ETHC_ElectricTHermostatControl | CW523(11) | Thermal | Olov Olsson
UHCF_UnderHoodCoolingFan | CW520.1(33) | Thermal | Long Qin
Note on F4: Dennis Kristensson: SWU Modell = 30 % MIL Test = 50 % HIL Test = 70 % Calibration = 90 % SWU Released = 100%

## Input Data
Date: |  |  |  | SWU Modell = 30% MIL Test = 50% HIL Test = 70 % Calibration = 90 % SWU Released = 100 %
Ver:
EMS C10TD
SWU | version | Domain | Owner | Status in % | Inital SW | 50% cal | 65% cal | 80% cal | 99% cal | 100%cal
Note on F5: Dennis Kristensson: SWU Modell = 30 % MIL Test = 50 % HIL Test = 70 % Calibration = 90 % SWU Released = 100%

## XXX SWU Input Data (hidden)
Date: |  |  |  | SWU Modell = 30% MIL Test = 50% HIL Test = 70 % Calibration = 90 % SWU Released = 100 %
Ver:
SWU | version | Domain | Owner | Status in % | Inital SW | 50% cal | 65% cal | 80% cal | 99% cal | 100%cal
[5 empty] | 2014-05-10 | 2014-08-22 | 2015-01-09 | 2015-05-01 | 2015-09-04 | 2015-09-30
BSWE_BasicSoftwareErrorhandling | CW523.1(3) | BSW | Fredrik Svan |  |  |  | X
CANE_AD_CANError | CW527.1(5) | Diagnostics | Robert Andersson |  |  |  | X
ComM_CommunicationsManager | CW512(2) | BSW | Robert Andersson | 30 |  | X
Dcm_EMS_EMS | CW526(6) | BSW | Robert Andersson | 30 |  |  | X
Dem_EMS_EMS | CW526(18) | BSW | Robert Andersson |  |  |  | X
DEME_DemExtension | CW527(12) | BSW | Robert Andersson |  |  |  | X
EcuM_EMS_EMS | CW512(3) | BSW | Jan Björn | 100 |  |  |  |  | X | X
EPOS_EnginePositioning | CW527(30) | BSW | Fredrik Svan | 70 | X
FACT_SwVersionInformation | CW527.1(12) | BSW | Mathias Stålek |  |  |  | X
FINC_FuelINjectorControl | CW526(10) | BSW | Fredrik Svan | 90 | X
HWDI_HardWareDiagnosticInfo | CW527(6) | BSW | Sebastian Wallman |  |  | X
ICCO_IgnitionCoilCOntrol | CW527(11) | BSW | Fredrik Svan |  |  |  |  | X
IMMO_AD_Immobilizer | CW527(11) | Torque | Fredrik Assarsson
KSDC_KnockSensorDeCoding | CW526(12) | BSW | Fredrik Svan |  |  | X
MEMO_MEMOry | CW527(6) | BSW | Fredrik Svan |  |  | X
MUTR_MonitoringUnitconTRoller | CW528(11) | BSW | Fredrik Svan |  |  |  | X
PWRM_AE_PowerMode | CW520(8) | Torque | Fredrik Behrendtz | 100 | X
BASS_BrakeSensorSystem | CSW20(20) | Torque | Emil Hilding | 30 | X
VSPE_VehicleSpeedEstimation | CW511(44) | Torque | Fredrik Assarsson |  |  | X
VODO_VehicleOdometer | CW525(7) | Torque | Fredrik Assarsson |  |  |  | X
VLOT_VehicleLOngitudinalTorque | CW520(18) | Torque | Fredrik Assarsson | 50 | X
AILM_AIrLiMits | CW449(9) | Combustion | Joel Lejonklou
ARES_AiREStimation | CW525(53) | Combustion | Per Andersson | 50 | X
CATC_CatalystControl | CW514(12) | Combustion | Fredrik Andersson |  |  | X
DYNO_DYNO | CW508(18) | Combustion | Andreas Gunnarsson |  | X
EARS_EngineArbitratedRotationalSpeed | CW503(10) | Combustion | Andreas Gunnarsson |  | X
ECOM_EngineControlManager | CW506.1(5) | Combustion | Andreas Gunnarsson
ECPC_ExhaustCamPostionControl | CW524(7) | Combustion | Per Darnfors |  |  | X
EITC_EngineIndicatedTorqueCalculation | CW521(35) | Combustion | Per Andersson | 30 | X
EOLT_EngineOiLTemperature | CW508(15) | Combustion | Per Darnfors |  |  | X
ETME_ExhaustTemperatureMeasurementAndEstimation | CW520(9) | Combustion | Joel Lejonklou |  |  | X
EXPE_ExhaustPressureEstimator | CSW21.2(3) | Thermal | Chunjiao Zhang | 30 |  | X
FINT_FuelINjectorTiming | CW520.1(30) | Diagnostics | Chunjiao Zhang | 50 | X
FPCR_FuelPumpControl | CW521.1(15) | Combustion | Tianfang Zhao | 50 | X
FUEL_Fuel | CW526(60) | Combustion | Claes Östberg | 50 | X
IASH_IntakeAirSystemHarmonization | CW519(17) | Combustion | Xue Lei |  |  | X
ICPC_IntakeCamPositionControl | CW524(26) | Combustion | Per Darnfors |  |  | X
ITCC_EMS_EMS_ICETorqueCapabilityAtCrankShaft | CW503.1(15) | Combustion | Joel Lejonklou |  |  | X
KOCO_KnOckCOntrol | CW525p1(18) | Combustion | Andreas Gunnarsson |  |  | X
OCTA_OctaneAdaption | CW525(9) | Combustion | Andreas Gunnarsson |  |  | X
OXYS_OxygenSensor | CW520(30) | Diagnostics | Liuchun Yang |  |  | X
PUCO_PUrgeCOntrol | CW526.1(34) | Combustion | Claes Östberg |  |  |  | X
SPRK_SPaRK | CW525(30) | Combustion | Andreas Gunnarsson | 70 | X
TPSC_ThrottlePositionSensingAndControl | CW519p1(28) | Combustion | Per Darnfors | 70 | X
VAVM_VAriableValveMaster | CW509(11) | Combustion | Per Darnfors |  |  |  | X
VLIM_VariableLengthIntakeManifold | CW518.2(8) | Combustion | Joel Lejonklou |  |  |  | X
ACBD_AC_ButtonDiagnosis | CW516(2) | Diagnostics | Stefan Bergström |  |  |  | X
ACOD_AC_ClutchControlDiagnosis | CW450(17) | Diagnostics | Mikael Andersson |  |  |  | X
ACPD_ACPressureDiagnosis | CW450(10) | Diagnostics | Feng Xu |  |  |  | X
ACRD_AirConditionRequestDiagnosis | CW513(12) | Diagnostics | Feng Xu |  |  |  | X
ACTD_AirCondTemperatureDiagnosis | CW450.2(20) | Diagnostics | Feng Xu |  |  |  | X
APSS_AcceleratorPedalSensorSystem | CW520.1(22) | Torque | Emil Hilding | 90 | X
BPPD_BrakePedalPositionDiagnosis | CW518(24) | Diagnostics | Stefan Bergström | 90 | X
BVAD_BrakeVAcuumSensorDiagnostic | CW516(17) | Diagnostics | Stefan Bergström |  |  | X
CACD_CAmControlDiagnosis | CW505(16) | Diagnostics | Stefan Bergström |  |  |  | X
CAMD_CamPositionDiagnosis | CW526.2(14) | Diagnostics | Stefan Bergström |  |  |  | X
CASD_CAm_exhaustSensorDiagnosis | CW526.1(3) | Diagnostics | Stefan Bergström |  |  |  | X
CATD_CatalyticEfficiencyDiagnosis | CW526(9) | Diagnostics | Ronnie Magnusson |  |  |  | X
CCSD_CruiseControlSystemDiagnosis | CW506(12) | Diagnostics | Feng Xu |  |  |  | X
CECD_CamExhaustControlDiagnosis | CW526.1(8) | Diagnostics | Stefan Bergström |  |  |  | X
CFMN_ControlFlowMonitoring | CW527(21) | Diagnostics | Fredrik Andersson |  |  |  | X
COLD_CoreOutofLimDiagnosis | CW525(27) | Diagnostics | Mikael Andersson |  |  |  | X
CPPD_ClutchPedalPositionDiagnosis | CW524(28) | Diagnostics | Mikael Andersson |  |  |  | X
CRAD_CrankAngleDiagnosis | CW509(15) | Diagnostics | Stefan Bergström |  |  |  | X
CSIN_CrashSignalINterpretation | CW519(13) | Torque | Ronnie Magnusson |  |  |  | X
CWTD_CoolantWaterTemperature_sensorDiagnosis | CW515(23) | Diagnostics | Mikael Andersson |  |  |  | X
ESDD_EngineSpeedDisplayDiagnosis | CW450(13) | Diagnostics | Feng Xu |  |  |  | X
ESID_AD_ExtendedServicesID | CW526.4(27) | Diagnostics | Mikael Andersson |  |  |  | X
ETHD_ElectricTHermostatDiagnosis | CW525(5) | Diagnostics | Stefan Bergström |  |  |  | X
EVPD_EvaporativePurgeValveDiagnosis | CW450.3(20) | Diagnostics | Long Qin |  |  |  | X
FAND_FanOutputDiagnosis | CW511(13) | Diagnostics | Cristian Salazar |  |  |  | X
FDMA_FunctionalDegradationMAnager | CW524.1(20) | Diagnostics | Christian Fransson |  |  |  | X
FPCD_FuelPumpControlDiagnosis | CW450.1(21) | Diagnostics | Cristian Salazar |  |  |  | X
FUID_FuelInjectorDiagnosis | CW450(12) | Diagnostics | Cristian Salazar |  |  |  | X
FUSD_FuelSystemDiagnosis | CW526(4) | Diagnostics | Cristian Salazar |  |  |  | X
HAMF_AD_HArdwareMonitoringFunction | CW522.3(5a1) | Diagnostics | Mikael Andersson |  |  | X
HOOD_HOOd switch Diagnos | CW516(13) | Diagnostics | Mikael Andersson |  |  |  | X
IGCD_IgnitionCoilDiagnosis | CW505.1(14) | Diagnostics | Long Qin |  |  |  | X
KNOD_KnockSensorDiagnosis | CW504(15) | Diagnostics | Stefan Bergström |  |  |  | X
LINE_EMS_EMS | CW525(4) | Diagnostics | Ronnie Magnusson | 100 | X
LSID_EMS_EMS | CW526.3(25) | Diagnostics | Mikael Andersson |  |  |  | X
MAPD_ManifoldAbsolutePressureDiagnosis | CW535.1(25) | Diagnostics | Feng Xu |  |  |  | X
MATD_MAnifoldTemperatureDiagnosis | CW508(33) | Diagnostics | Long Qin |  |  |  | X
MILD_MalfunctionIndicatorLampDiagnosis | CW516(11) | Diagnostics | Stefan Bergström |  |  |  | X
MSFD_MisfireDiagnosis | CW525(7) | Diagnostics | Fredrik Andersson |  |  |  | X
NGSD_NeutralGearSensorDiagnosis | CW521(4) | Diagnostics | Stefan Bergström |  |  |  | X
OSDD_OxygenSensorDeteriorationDiagnosis | CW525(17) | Diagnostics | Cristian Salazar |  |  |  | X
OSHD_OxygenSensorHeaterDiagnosis | CW525(15) | Diagnostics | Cristian Salazar |  |  |  | X
PRCD_PowerRelayControlDiagnosis | CW525.1(2) | Diagnostics | Feng Xu |  |  |  | X
SRCD_StarterRelayCircuitDiagnosis | CW526(21) | Diagnostics | Cristian Salazar |  |  |  | X
SSSD_StartStopSensorDiagnosis | CW522.1(7) | Diagnostics | Mikael Andersson |  |  |  | X
SYVD_SystemVoltageDiagnosis | CW513(20) | Diagnostics | Cristian Salazar |  |  |  | X
TPSD_ThrottlePositionDiagnosis | CW526(19) | Diagnostics | Stefan Bergström |  |  |  | X
V5RD_Regulated5VoltDiagnosis | CW450(19) | Diagnostics | Cristian Salazar |  |  |  | X
VILD_VariableIntakeLengthDiagnosis | CW507.1(4) | Diagnostics | Stefan Bergström |  |  |  | X
ACCP_AcceleratorPedalmap | CW504(27) | Torque | Emil Hilding | 50 | X
ACRC_AirConditionRelayControl | CW525(14) | Torque | Kai Wang |  |  |  | X
AJTC_AntiJerkTorqueControl | CW521(6) | Torque | Magnus Källvik |  |  | X
ATLC_AutomaticTransmissionLoadCalculation | CW519(2) | Torque | Fredrik Behrendtz |  |  | X
CACE_ControllerAfterrunAndCanEnable | CW514(36a7) | Torque | Fredrik Behrendtz | 30 | X
CIDI_CruiseIndicatorDIsplay | CW450.1(5) | Torque | Long Qin |  |  |  | X
CRSC_CruiseControl | CW523(34) | Torque | Tianfang Zhao |  |  |  | X
DCWT_DirectionControlWheelTorque | CW506(21) | Torque | Fredrik Behrendtz |  |  | X
DIPR_DIfferentialPRotection | CW518(8) | Torque | Olof Martander |  |  |  | X
DOSR_DetermineOptimalSystemRequest | CW510_NH(34a4) | Torque | Magnus Källvik |  |  | X
DPSC_DeterminePropulsionSystemCapability | CW520.1(37) | Torque | Emil Hilding |  |  | X
DTOS_DriveabilityTorqueShaping | CW525(27) | Torque | Magnus Källvik |  |  |  | X
ESDI_EngineSpeedDIsplay | CW519(4) | Torque | Feng Xu |  |  |  | X
FCDI_FuelConsumptionDIsplay | CW509.3(8) | Torque | Feng Xu |  |  |  | X
GEVC_GEneratorVoltageControl | CW514.1(18) | Torque | Kai Wang |  |  | X
HETE_HybridElectricTorqueExecutor | CW448(49) | Torque | Johan Larsson |  |  | X
LVEM_LowVoltageEnergyManagement | CW515(37) | Torque | Olof Martander |  |  | X
MAVS_MaximumVehicleSpeed | CW515.1(32) | Torque | Olof Martander |  |  |  | X
PDLS_BothPedalShaping | CW450(20) | Torque | Emil Hilding | 50 | X
POLC_P1LoadCalculation | CW514(18) | Torque | Fredrik Behrendtz | 50 | X
PORS_P1RotationalSpeed | CSW25.5(19) | Torque | Fredrik Behrendtz | 50 | X
SILT_AD_SoftwareInterfaceLevelTwo | CW523(6) | Diagnostics | Christian Fransson |  |  |  | X
SPAR_EMS_EMS | CW521(10) | Torque | Fredrik Behrendtz | 50 | x | x | X
SSDI_StartStopDisplayInformation | CW520.2(7) | Torque | Emil Hilding |  |  |  | X
SSDL_StartStopDeterminationLogic | CW520(55) | Torque | Johan Larsson |  |  |  | X
SSSC_StartStopSequenceControl | CW524(42) | Torque | Johan Larsson |  |  |  | X
SSSM_StartStopStateMachine | CW503(36) | Torque | Johan Larsson |  |  |  | X
SSTD_StartStopTypeDetermination | CW522(19) | Torque | Johan Larsson |  |  |  | X
STCW_SystemTorqueCapabilities | CW519(39) | Torque | Magnus Källvik | 50 | X
SWIN_EMS_EMS | CW528(61) | Torque | Fredrik Behrendtz | 50 | X
TIRC_WheelToTransmissionInputandResponseControl | CW514(28) | Torque | Magnus Källvik | 50 | X
TISC_TransmissionInputSpeedControl | CW521.1(59) | Torque | Johan Larsson | 50 | X
TQMS_TorqueMonitoring | CW526.2(47) | Diagnostics | Christian Fransson |  |  |  | X
VTAR_VehicleTorqueArbitration | CW509(26) | Torque | Fredrik Behrendtz | 50 | X
WTDA_WheelTorqueDistribution | CSW20(9) | Torque | Magnus Källvik | 50 | X
GERC_GearEstimationAndRatioCalulation | CW511(29) | Torque | Per Darnfors | 50 | X
TCAP_TransmissionCapabilities | CW520(26) | Torque | Christian Fransson | 50 | X
TTSS_TransmissionTorqueandSpeedSupport | CW520(32a4) | Torque | Per Darnfors |  |  | X
CTDI_CoolantTempDIsplay | CW519(9) | Torque | Long Qin |  |  |  | X
ETHC_ElectricTHermostatControl | CW523(11) | Thermal | Olov Olsson | 30 |  | X
UHCF_UnderHoodCoolingFan | CW520.1(33) | Thermal | Long Qin | 70 | X
Note on F4: Dennis Kristensson: SWU Modell = 30 % MIL Test = 50 % HIL Test = 70 % Calibration = 90 % SWU Released = 100%

## XX SWU Input Data (hidden)
Date: |  |  |  | SWU Modell = 30% MIL Test = 50% HIL Test = 70 % Calibration = 90 % SWU Released = 100 %
Ver:
SWU | version | Domain | Owner | Status in % | Inital SW | 50% cal | 65% cal | 80% cal | 99% cal | 100%cal
[5 empty] | 2014-05-10 | 2014-08-22 | 2015-01-09 | 2015-05-01 | 2015-09-04 | 2015-09-30
BSWE_BasicSoftwareErrorhandling | CW523.1(3) | BSW | Fredrik Svan |  |  |  | X
CANE_AD_CANError | CW527.1(5) | Diagnostics | Robert Andersson |  |  |  | X
ComM_CommunicationsManager | CW512(2) | BSW | Robert Andersson | 30 |  | X
Dcm_EMS_EMS | CW526(6) | BSW | Robert Andersson | 30 |  |  | X
Dem_EMS_EMS | CW526(18) | BSW | Robert Andersson |  |  |  | X
DEME_DemExtension | CW527(12) | BSW | Robert Andersson |  |  |  | X
EcuM_EMS_EMS | CW512(3) | BSW | Jan Björn | 100 |  |  |  |  | X | X
EPOS_EnginePositioning | CW527(30) | BSW | Fredrik Svan | 70 | X
FACT_SwVersionInformation | CW527.1(12) | BSW | Mathias Stålek |  |  |  | X
FINC_FuelINjectorControl | CW526(10) | BSW | Fredrik Svan | 90 | X
HWDI_HardWareDiagnosticInfo | CW527(6) | BSW | Sebastian Wallman |  |  | X
ICCO_IgnitionCoilCOntrol | CW527(11) | BSW | Fredrik Svan |  |  |  |  | X
IMMO_AD_Immobilizer | CW527(11) | Torque | Fredrik Assarsson
KSDC_KnockSensorDeCoding | CW526(12) | BSW | Fredrik Svan |  |  | X
MEMO_MEMOry | CW527(6) | BSW | Fredrik Svan |  |  | X
MUTR_MonitoringUnitconTRoller | CW528(11) | BSW | Fredrik Svan |  |  |  | X
PWRM_AE_PowerMode | CW520(8) | Torque | Fredrik Behrendtz | 100 | X
BASS_BrakeSensorSystem | CSW20(20) | Torque | Emil Hilding | 30 | X
VSPE_VehicleSpeedEstimation | CW511(44) | Torque | Fredrik Assarsson |  |  | X
VODO_VehicleOdometer | CW525(7) | Torque | Fredrik Assarsson |  |  |  | X
VLOT_VehicleLOngitudinalTorque | CW520(18) | Torque | Fredrik Assarsson | 50 | X
AILM_AIrLiMits | CW449(9) | Combustion | Joel Lejonklou
ARES_AiREStimation | CW525(53) | Combustion | Per Andersson | 50 | X
CATC_CatalystControl | CW514(12) | Combustion | Fredrik Andersson |  |  | X
DYNO_DYNO | CW508(18) | Combustion | Andreas Gunnarsson |  | X
EARS_EngineArbitratedRotationalSpeed | CW503(10) | Combustion | Andreas Gunnarsson |  | X
ECOM_EngineControlManager | CW506.1(5) | Combustion | Andreas Gunnarsson
ECPC_ExhaustCamPostionControl | CW524(7) | Combustion | Per Darnfors |  |  | X
EITC_EngineIndicatedTorqueCalculation | CW521(35) | Combustion | Per Andersson | 30 | X
EOLT_EngineOiLTemperature | CW508(15) | Combustion | Per Darnfors |  |  | X
ETME_ExhaustTemperatureMeasurementAndEstimation | CW520(9) | Combustion | Joel Lejonklou |  |  | X
EXPE_ExhaustPressureEstimator | CSW21.2(3) | Thermal | Chunjiao Zhang | 30 |  | X
FINT_FuelINjectorTiming | CW520.1(30) | Diagnostics | Chunjiao Zhang | 50 | X
FPCR_FuelPumpControl | CW521.1(15) | Combustion | Tianfang Zhao | 50 | X
FUEL_Fuel | CW526(60) | Combustion | Claes Östberg | 50 | X
IASH_IntakeAirSystemHarmonization | CW519(17) | Combustion | Xue Lei |  |  | X
ICPC_IntakeCamPositionControl | CW524(26) | Combustion | Per Darnfors |  |  | X
ITCC_EMS_EMS_ICETorqueCapabilityAtCrankShaft | CW503.1(15) | Combustion | Joel Lejonklou |  |  | X
KOCO_KnOckCOntrol | CW525p1(18) | Combustion | Andreas Gunnarsson |  |  | X
OCTA_OctaneAdaption | CW525(9) | Combustion | Andreas Gunnarsson |  |  | X
OXYS_OxygenSensor | CW520(30) | Diagnostics | Liuchun Yang |  |  | X
PUCO_PUrgeCOntrol | CW526.1(34) | Combustion | Claes Östberg |  |  |  | X
SPRK_SPaRK | CW525(30) | Combustion | Andreas Gunnarsson | 70 | X
TPSC_ThrottlePositionSensingAndControl | CW519p1(28) | Combustion | Per Darnfors | 70 | X
VAVM_VAriableValveMaster | CW509(11) | Combustion | Per Darnfors |  |  |  | X
VLIM_VariableLengthIntakeManifold | CW518.2(8) | Combustion | Joel Lejonklou |  |  |  | X
ACBD_AC_ButtonDiagnosis | CW516(2) | Diagnostics | Stefan Bergström |  |  |  | X
ACOD_AC_ClutchControlDiagnosis | CW450(17) | Diagnostics | Mikael Andersson |  |  |  | X
ACPD_ACPressureDiagnosis | CW450(10) | Diagnostics | Feng Xu |  |  |  | X
ACRD_AirConditionRequestDiagnosis | CW513(12) | Diagnostics | Feng Xu |  |  |  | X
ACTD_AirCondTemperatureDiagnosis | CW450.2(20) | Diagnostics | Feng Xu |  |  |  | X
APSS_AcceleratorPedalSensorSystem | CW520.1(22) | Torque | Emil Hilding | 90 | X
BPPD_BrakePedalPositionDiagnosis | CW518(24) | Diagnostics | Stefan Bergström | 90 | X
BVAD_BrakeVAcuumSensorDiagnostic | CW516(17) | Diagnostics | Stefan Bergström |  |  | X
CACD_CAmControlDiagnosis | CW505(16) | Diagnostics | Stefan Bergström |  |  |  | X
CAMD_CamPositionDiagnosis | CW526.2(14) | Diagnostics | Stefan Bergström |  |  |  | X
CASD_CAm_exhaustSensorDiagnosis | CW526.1(3) | Diagnostics | Stefan Bergström |  |  |  | X
CATD_CatalyticEfficiencyDiagnosis | CW526(9) | Diagnostics | Ronnie Magnusson |  |  |  | X
CCSD_CruiseControlSystemDiagnosis | CW506(12) | Diagnostics | Feng Xu |  |  |  | X
CECD_CamExhaustControlDiagnosis | CW526.1(8) | Diagnostics | Stefan Bergström |  |  |  | X
CFMN_ControlFlowMonitoring | CW527(21) | Diagnostics | Fredrik Andersson |  |  |  | X
COLD_CoreOutofLimDiagnosis | CW525(27) | Diagnostics | Mikael Andersson |  |  |  | X
CPPD_ClutchPedalPositionDiagnosis | CW524(28) | Diagnostics | Mikael Andersson |  |  |  | X
CRAD_CrankAngleDiagnosis | CW509(15) | Diagnostics | Stefan Bergström |  |  |  | X
CSIN_CrashSignalINterpretation | CW519(13) | Torque | Ronnie Magnusson |  |  |  | X
CWTD_CoolantWaterTemperature_sensorDiagnosis | CW515(23) | Diagnostics | Mikael Andersson |  |  |  | X
ESDD_EngineSpeedDisplayDiagnosis | CW450(13) | Diagnostics | Feng Xu |  |  |  | X
ESID_AD_ExtendedServicesID | CW526.4(27) | Diagnostics | Mikael Andersson |  |  |  | X
ETHD_ElectricTHermostatDiagnosis | CW525(5) | Diagnostics | Stefan Bergström |  |  |  | X
EVPD_EvaporativePurgeValveDiagnosis | CW450.3(20) | Diagnostics | Long Qin |  |  |  | X
FAND_FanOutputDiagnosis | CW511(13) | Diagnostics | Cristian Salazar |  |  |  | X
FDMA_FunctionalDegradationMAnager | CW524.1(20) | Diagnostics | Christian Fransson |  |  |  | X
FPCD_FuelPumpControlDiagnosis | CW450.1(21) | Diagnostics | Cristian Salazar |  |  |  | X
FUID_FuelInjectorDiagnosis | CW450(12) | Diagnostics | Cristian Salazar |  |  |  | X
FUSD_FuelSystemDiagnosis | CW526(4) | Diagnostics | Cristian Salazar |  |  |  | X
HAMF_AD_HArdwareMonitoringFunction | CW522.3(5a1) | Diagnostics | Mikael Andersson |  |  | X
HOOD_HOOd switch Diagnos | CW516(13) | Diagnostics | Mikael Andersson |  |  |  | X
IGCD_IgnitionCoilDiagnosis | CW505.1(14) | Diagnostics | Long Qin |  |  |  | X
KNOD_KnockSensorDiagnosis | CW504(15) | Diagnostics | Stefan Bergström |  |  |  | X
LINE_EMS_EMS | CW525(4) | Diagnostics | Ronnie Magnusson | 100 | X
LSID_EMS_EMS | CW526.3(25) | Diagnostics | Mikael Andersson |  |  |  | X
MAPD_ManifoldAbsolutePressureDiagnosis | CW535.1(25) | Diagnostics | Feng Xu |  |  |  | X
MATD_MAnifoldTemperatureDiagnosis | CW508(33) | Diagnostics | Long Qin |  |  |  | X
MILD_MalfunctionIndicatorLampDiagnosis | CW516(11) | Diagnostics | Stefan Bergström |  |  |  | X
MSFD_MisfireDiagnosis | CW525(7) | Diagnostics | Fredrik Andersson |  |  |  | X
NGSD_NeutralGearSensorDiagnosis | CW521(4) | Diagnostics | Stefan Bergström |  |  |  | X
OSDD_OxygenSensorDeteriorationDiagnosis | CW525(17) | Diagnostics | Cristian Salazar |  |  |  | X
OSHD_OxygenSensorHeaterDiagnosis | CW525(15) | Diagnostics | Cristian Salazar |  |  |  | X
PRCD_PowerRelayControlDiagnosis | CW525.1(2) | Diagnostics | Feng Xu |  |  |  | X
SRCD_StarterRelayCircuitDiagnosis | CW526(21) | Diagnostics | Cristian Salazar |  |  |  | X
SSSD_StartStopSensorDiagnosis | CW522.1(7) | Diagnostics | Mikael Andersson |  |  |  | X
SYVD_SystemVoltageDiagnosis | CW513(20) | Diagnostics | Cristian Salazar |  |  |  | X
TPSD_ThrottlePositionDiagnosis | CW526(19) | Diagnostics | Stefan Bergström |  |  |  | X
V5RD_Regulated5VoltDiagnosis | CW450(19) | Diagnostics | Cristian Salazar |  |  |  | X
VILD_VariableIntakeLengthDiagnosis | CW507.1(4) | Diagnostics | Stefan Bergström |  |  |  | X
ACCP_AcceleratorPedalmap | CW504(27) | Torque | Emil Hilding | 50 | X
ACRC_AirConditionRelayControl | CW525(14) | Torque | Kai Wang |  |  |  | X
AJTC_AntiJerkTorqueControl | CW521(6) | Torque | Magnus Källvik |  |  | X
ATLC_AutomaticTransmissionLoadCalculation | CW519(2) | Torque | Fredrik Behrendtz |  |  | X
CACE_ControllerAfterrunAndCanEnable | CW514(36a7) | Torque | Fredrik Behrendtz | 30 | X
CIDI_CruiseIndicatorDIsplay | CW450.1(5) | Torque | Long Qin |  |  |  | X
CRSC_CruiseControl | CW523(34) | Torque | Tianfang Zhao |  |  |  | X
DCWT_DirectionControlWheelTorque | CW506(21) | Torque | Fredrik Behrendtz |  |  | X
DIPR_DIfferentialPRotection | CW518(8) | Torque | Olof Martander |  |  |  | X
DOSR_DetermineOptimalSystemRequest | CW510_NH(34a4) | Torque | Magnus Källvik |  |  | X
DPSC_DeterminePropulsionSystemCapability | CW520.1(37) | Torque | Emil Hilding |  |  | X
DTOS_DriveabilityTorqueShaping | CW525(27) | Torque | Magnus Källvik |  |  |  | X
ESDI_EngineSpeedDIsplay | CW519(4) | Torque | Feng Xu |  |  |  | X
FCDI_FuelConsumptionDIsplay | CW509.3(8) | Torque | Feng Xu |  |  |  | X
GEVC_GEneratorVoltageControl | CW514.1(18) | Torque | Kai Wang |  |  | X
HETE_HybridElectricTorqueExecutor | CW448(49) | Torque | Johan Larsson |  |  | X
LVEM_LowVoltageEnergyManagement | CW515(37) | Torque | Olof Martander |  |  | X
MAVS_MaximumVehicleSpeed | CW515.1(32) | Torque | Olof Martander |  |  |  | X
PDLS_BothPedalShaping | CW450(20) | Torque | Emil Hilding | 50 | X
POLC_P1LoadCalculation | CW514(18) | Torque | Fredrik Behrendtz | 50 | X
PORS_P1RotationalSpeed | CSW25.5(19) | Torque | Fredrik Behrendtz | 50 | X
SILT_AD_SoftwareInterfaceLevelTwo | CW523(6) | Diagnostics | Christian Fransson |  |  |  | X
SPAR_EMS_EMS | CW521(10) | Torque | Fredrik Behrendtz | 50 | x | x | X
SSDI_StartStopDisplayInformation | CW520.2(7) | Torque | Emil Hilding |  |  |  | X
SSDL_StartStopDeterminationLogic | CW520(55) | Torque | Johan Larsson |  |  |  | X
SSSC_StartStopSequenceControl | CW524(42) | Torque | Johan Larsson |  |  |  | X
SSSM_StartStopStateMachine | CW503(36) | Torque | Johan Larsson |  |  |  | X
SSTD_StartStopTypeDetermination | CW522(19) | Torque | Johan Larsson |  |  |  | X
STCW_SystemTorqueCapabilities | CW519(39) | Torque | Magnus Källvik | 50 | X
SWIN_EMS_EMS | CW528(61) | Torque | Fredrik Behrendtz | 50 | X
TIRC_WheelToTransmissionInputandResponseControl | CW514(28) | Torque | Magnus Källvik | 50 | X
TISC_TransmissionInputSpeedControl | CW521.1(59) | Torque | Johan Larsson | 50 | X
TQMS_TorqueMonitoring | CW526.2(47) | Diagnostics | Christian Fransson |  |  |  | X
VTAR_VehicleTorqueArbitration | CW509(26) | Torque | Fredrik Behrendtz | 50 | X
WTDA_WheelTorqueDistribution | CSW20(9) | Torque | Magnus Källvik | 50 | X
GERC_GearEstimationAndRatioCalulation | CW511(29) | Torque | Per Darnfors | 50 | X
TCAP_TransmissionCapabilities | CW520(26) | Torque | Christian Fransson | 50 | X
TTSS_TransmissionTorqueandSpeedSupport | CW520(32a4) | Torque | Per Darnfors |  |  | X
CTDI_CoolantTempDIsplay | CW519(9) | Torque | Long Qin |  |  |  | X
ETHC_ElectricTHermostatControl | CW523(11) | Thermal | Olov Olsson | 30 |  | X
UHCF_UnderHoodCoolingFan | CW520.1(33) | Thermal | Long Qin | 70 | X
Note on F4: Dennis Kristensson: SWU Modell = 30 % MIL Test = 50 % HIL Test = 70 % Calibration = 90 % SWU Released = 100%

## Calculations
A15 | NR of SWU´s | Sum of total % | A15 | Nr of SWU´s | Sum of Total %
BSW | #REF! | #REF! | Inital SW | 1
Torque | #REF! | #REF! | 50% Cal | 0
Combustion | #REF! | #REF! | 65 % Cal | 0
Diagnostics | #REF! | #REF! | 80 % Cal | 0
Thermal | #REF! | #REF! | 99 % Cal | 0
|  |  | 100 % Cal | 0
C10TD | NR of SWU´s | Sum of total % | C10TD | Nr of SWU´s | Sum of Total %
BSW | 0 | #DIV/0! | Inital SW | 0 | #DIV/0!
Torque | 0 | #DIV/0! | 50% Cal | 0 | #DIV/0!
Combustion | 0 | #DIV/0! | 65 % Cal | 0 | #DIV/0!
Diagnostics | 0 | #DIV/0! | 80 % Cal | 0 | #DIV/0!
Thermal | 0 | #DIV/0! | 99 % Cal | 0 | #DIV/0!
|  |  | 100 % Cal | 0 | #DIV/0!
XXX | NR of SWU´s | Sum of total % | XXX | Nr of SWU´s | Sum of Total %
BSW | #REF! | #REF! | Inital SW | 32
Torque | #REF! | #REF! | 50% Cal | 29
Combustion | #REF! | #REF! | 65 % Cal | 70
Diagnostics | #REF! | #REF! | 80 % Cal | 1
Thermal | #REF! | #REF! | 99 % Cal | 1
|  |  | 100 % Cal | 1
|  |  | XX | Nr of SWU´s | Sum of Total %
|  |  | Inital SW | 32
|  |  | 50% Cal | 29
|  |  | 65 % Cal | 70
|  |  | 80 % Cal | 1
|  |  | 99 % Cal | 1
|  |  | 100 % Cal | 1